## Slide 1
Improving Feedback to Learners & Reducing Teacher Workload Summary Report February 2019
Project Sponsor ERW
Consortia Project Team: Gwyn Pleming GwE Delyth Jones ERW Louise Muteham CSC Ed Pryce EAS
Katy Edwards & Sarah Cason Palmerston Primary Cross Regional Project Manager Helen Richards
Background
Over the past few years a number of reports, such as, the Education Workforce Survey (April 2017) and Marking Policy Review group (March 2017), have highlighted that excessive workload is impacting teacher wellbeing and retention and recruitment and taking teachers away from their core task of improving learner outcomes. Effective assessment is at the heart of high quality learning and teaching. It will be core to the successful implementation of the new curriculum for Wales.
Issue
“Marking has evolved into an unhelpful burden for teachers where the time it takes is not repaid in positive impact on pupil’ progress’’ (Marking Review Policy Review Group DFE March 2016)
Purpose
To establish an ongoing programme to increasingly improve learner feedback and reduce teacher workload
A guide for school leaders and teachers
Guide developed in collaboration with ESTYN & Welsh Government
Launched at Palmerston Primary by Cabinet Secretary Kirsty Williams September 2017
The Guide was simultaneously uploaded to the ESTYN websites with signposting from all regional consortia, Welsh Government and Discover teaching sites and hard copies of the poster and leaflet disseminated to all schools in Wales
Animations developed & shared across regional consortia and Discover Teaching social media networks
Phase I : Progress and actions completed to date
Professional Learning Model
Cross regional collaboration to develop a National Professional Learning Module to support implementation of the guidance and develop pedagogical practice related to learner feedback and assessment for learning principles.
Programme core objective = “to improve teachers use of effective feedback so it has the least impact on their workload but ensure the most effect on pupil progress”
Modules will develop schools’ understanding of how they can develop active learners, who can reflect on and evaluate their own and others progress, in order to become effective, independent learners
Programme awareness raising presentation developed and delivered to all Consortia Challenge Advisers. This opportunity was also offered to all head teachers and was well attended across all regions.
Train the Trainer events were held across the regions, consistency of implementation ensured through the delivery of all sessions by the consortia cross regional project team.
Programme delivery schedules in place and commenced in all regions.
Where previously 4 separate regional programmes would have been developed, working in collaboration to develop and deliver one programme has led to significantly improved value for money, efficiency and consistency of message.
To date 65 trainers have been developed and 201 Headteachers / Leaders completed training

## Slide 2
Supporting Resources Developed
Hwb location created as repository for programme supporting resources.
To encourage course attendance, access to hwb location is granted once training is completed.
185 members to date
Resources include - Programme Modules 1-4 - Best practice case studies
- Trinity St David’s research project - Suggested reading and research
A sample of complementary & supporting regional work informing project & programme development
ERW case study – 500 school visits by Challenge Advisers. Compulsory focus on the evaluation of feedback on pupil progress whist addressing the reduced workload agenda. Incorporated into initial awareness raising presentation delivered to head teachers and challenge advisers.
GwE – two year rolling programme of work with Shirley Clark, to involve all regional schools working in 3 tiers, 27 schools with 54 practitioners selected for first phase utilising classroom action based research to support teachers in developing AFL practice and pedagogical approach. These will then be lead schools for the project duration.
Five school improvement groups within CSC are working collaboratively to improve formative assessment. A proportion of these schools received training from Dylan William & Shirley Clark resulting in a best practice sharing event attended by over 70 practitioners and school leaders.
EAS – Formation of a Regional HT Reducing Workload Group to review all ‘requests’ from the EAS for reasonableness and purpose. Requirements from the EAS for accountability requests have been reviewed as a result of this group. 17/18 funding for circa 50 schools (Learning Network Schools) to provide support and training for other schools in a number of aspects, including learner feedback.
Phase II March 2018 - 2019
Continuation of regional roll out of professional learning module.
Termly review of programme incorporating recommendations from survey monkey feedback and cross reference against professional teaching and leadership standards. First workshop scheduled for May 2018.
Further development of promotion and training in the use of digital tools, through an additional module
Development of resource materials for use as inset materials
Consortia Communications team to develop rolling programme to promote key messages.
Engagement with ITE colleges with aim of incorporation of programme into course content
Development of best practice video case studies
Utilisation of Challenge Adviser & regional teams to gather impact of training & materials at class room level
Explore use of guidance by ESTYN inspectors through focus group interviews
Focus group interviews with practicioners, school leaders and learners to start to identify impact of the guidance and supporting programme.
Programme initial evaluation - Survey Monkey
Survey monkey has been utilised to evaluate impact of course content and delivery – evaluation of first 60 attendees has elicited overwhelmingly positive responses, for example, when asked to what degree “the content will impact and improve current practice within my school” an average score of 4.55 was achieved ( 4 = agree & 5 strongly agree)
When asked following programme attendance “how could your increased knowledge or skills impact on learner outcomes within your schools?” comments included
“The training will help staff understand what reduced workload means. It will also make feedback to pupils more effective thus moving their learning and understanding forward.”
“More timely and varied assessment within lessons = less time spent on marking. As a result, more time to plan and prepare effective learning experiences.”
For more information contact Project Manager for Cross Regional Projects helen.richards@sewaleseas.org.uk